## KPI Dashboard
YoungXCode — KPI Dashboard
Auto-calculated from Clients, Projects, Tasks, Invoices sheets. Update target values (yellow) as needed.
KPI | Formula / Calculation Method | Current Value | Target | Status | Category
Monthly Recurring Revenue (MRR) | Total Invoiced Amount (incl. GST) / Number of Active Months | 877578.4618 | 1000000 | Below Target | Revenue
Average Project Value | AVERAGE(Project Budget) across all projects | 1169068.9212 | 1200000 | Below Target | Revenue
Invoice Collection Rate | SUM(Paid Invoices Total) / SUM(Total Invoiced) x 100 | 51.7% | 85% | Below Target | Revenue
Overdue Amount | SUM(Total Amount) where Payment Status is Overdue/Unpaid/Partially Paid AND Due Date < Today | 14412610.39 | 500000 | Above Target | Revenue
On-Time Delivery Rate | COUNT(Completed Projects, Actual End <= Deadline) / COUNT(Completed Projects) x 100 | 29.17% | 90% | Below Target | Project
Average Project Duration (days) | AVERAGE(Actual End Date - Start Date) for Completed Projects | 141.4894 | 120 | Above Target | Project
Budget Overrun Rate | COUNT(Projects where Amount Spent > Budget) / COUNT(Total Projects) x 100 | 28.75% | 15% | Above Target | Project
Task Completion Rate | COUNT(Tasks where Status = Completed) / COUNT(Total Tasks) x 100 | 78.67% | 85% | Below Target | Team
Average Hours per Task | AVERAGE(Actual Hours) across all tasks | 38.6717 | 35 | Above Target | Team
Team Utilization % | SUM(Actual Hours) / SUM(Estimated Hours) x 100 | 97.96% | 90% | On Track | Team
Client Retention Rate | COUNT(Clients with Total Projects >= 1) / COUNT(Total Clients) x 100 | 84% | 80% | On Track | Client
Average Projects per Client | AVERAGE(Total Projects per Client) | 1.6 | 2 | Below Target | Client

## Calc
Helper Calculations
Label | Value
Total Invoiced (incl GST) | 29837667.7
Active Months Span | 34
Total Paid Amount | 15425057.31
Total Overdue Amount | 14412610.39
Completed Projects Count | 48
On-Time Completed Count | 14
Sum Duration (Completed, days) | 6650
Completed Projects with Valid End Date | 47
Total Projects Count | 80
Overrun Projects Count | 23
Total Tasks Count | 300
Completed Tasks Count | 236
Sum Actual Hours | 11601.5
Sum Estimated Hours | 11843.2
Total Clients Count | 50
Clients with Projects >=1 | 42

## Clients
client_id | client_name | city | industry | join_date | total_projects | total_revenue
CL1000 | Apex Systems | Lucknow | Logistics | 2022-06-18 | 1 | 1150740.85
CL1001 | Nova Corp | Bangalore | E-Commerce | 2020-08-17 | 2 | 854257.39
CL1002 | Pixel Works | Chennai | Real Estate | 2023-07-16 | 4 | 489884.4
CL1003 | Quantum Labs | Mumbai | Media | 2020-09-28 | 0 | 1492621.23
CL1004 | Grand Systems | Bangalore | Retail | 2023-07-12 | 2 | 3173088.66
CL1005 | Apex Corp | Lucknow | Retail | 2024-06-08 | 3 | 209383.83
CL1006 | Cloud Technologies | Pune | Education | 2021-08-08 | 1 | 0
CL1007 | Tech Hub | Indore | Fintech | 2022-10-07 | 2 | 0
CL1008 | Swift Solutions | Indore | Media | 2022-12-12 | 2 | 80360.31
CL1009 | Nova Systems | Surat | Hospitality | 2024-10-20 | 2 | 0
CL1010 | Quantum Works | Bangalore | Education | 2024-01-22 | 1 | 763382.97
CL1011 | Crest Hub | Ahmedabad | Healthcare | 2025-09-18 | 0 | 2248114.24
CL1012 | Nova Technologies | Mumbai | Education | 2021-03-15 | 1 | 0
CL1013 | Quantum Corp | Lucknow | Hospitality | 2021-10-17 | 1 | 324340.97
CL1014 | Crest Group | Chennai | Hospitality | 2020-09-17 | 4 | 781709.01
CL1015 | Quantum Enterprises | Kolkata | Real Estate | 2025-04-01 | 0 | 1173979.01
CL1016 | Vivid Industries | Lucknow | Healthcare | 2020-02-17 | 2 | 668547.84
CL1017 | Royal Solutions | Lucknow | Logistics | 2022-12-28 | 0 | 331944.15
CL1018 | Royal Labs | Pune | Hospitality | 2021-04-01 | 1 | 0
CL1019 | Grand Group | Ahmedabad | E-Commerce | 2021-10-09 | 2 | 362559.05
CL1020 | Urban Industries | Kolkata | Education | 2022-12-14 | 1 | 1466406.75
CL1021 | Bright Works | Mumbai | Real Estate | 2025-09-10 | 2 | 0
CL1022 | Royal Ventures | Surat | Fintech | 2025-09-10 | 1 | 0
CL1023 | Tech Systems | Hyderabad | Education | 2021-09-18 | 0 | 0
CL1024 | Swift Systems | Jaipur | Media | 2025-12-12 | 2 | 524774.19
CL1025 | Urban Ventures | Ahmedabad | E-Commerce | 2023-08-20 | 0 | 0
CL1026 | Grand Enterprises | Hyderabad | Real Estate | 2021-04-03 | 3 | 353367.77
CL1027 | Crest Systems | Jaipur | Fintech | 2022-09-07 | 1 | 221224.7
CL1028 | Cloud Group | Mumbai | Retail | 2020-11-18 | 2 | 856336.98
CL1029 | Tech Technologies | Kolkata | Education | 2020-10-10 | 2 | 0
CL1030 | Pixel Net | Lucknow | Retail | 2021-06-09 | 1 | 0
CL1031 | Vivid Ventures | Pune | Manufacturing | 2021-11-07 | 1 | 600549.69
CL1032 | Vivid Works | Bangalore | Manufacturing | 2024-09-29 | 1 | 968199.5
CL1033 | Nova Net | Indore | Real Estate | 2022-09-01 | 2 | 1786447.86
CL1034 | Quantum Industries | Lucknow | Logistics | 2024-06-22 | 2 | 896886.67
CL1035 | Tech Works | Kolkata | Retail | 2024-11-29 | 5 | 812017.98
CL1036 | Silver Systems | Bangalore | Fintech | 2021-05-10 | 1 | 1294689.18
CL1037 | Swift Industries | Hyderabad | E-Commerce | 2020-09-19 | 2 | 0
CL1038 | Bharat Net | Surat | Fintech | 2022-07-31 | 1 | 848061.91
CL1039 | Silver Ventures | Mumbai | E-Commerce | 2020-01-30 | 2 | 636659.64
CL1040 | Bright Ventures | Mumbai | E-Commerce | 2022-07-26 | 2 | 0
CL1041 | Urban Works | Mumbai | Manufacturing | 2023-09-15 | 0 | 1285647.9
CL1042 | Apex Industries | Pune | Retail | 2022-09-01 | 2 | 0
CL1043 | Grand Net | Kolkata | Education | 2022-05-27 | 1 | 1370420.38
CL1044 | Vivid Net | Bangalore | Retail | 2025-04-20 | 2 | 0
CL1045 | Bright Technologies | Bangalore | Healthcare | 2024-07-25 | 0 | 64005.81
CL1046 | Grand Works | Lucknow | Hospitality | 2021-02-01 | 2 | 395338.83
CL1047 | Bright Enterprises | Chennai | Hospitality | 2023-12-22 | 2 | 0
CL1048 | Cloud Net | Indore | E-Commerce | 2025-03-27 | 4 | 666661.28
CL1049 | Grand Technologies | Jaipur | Hospitality | 2021-02-07 | 2 | 685056.77

## Projects
project_id | project_name | client_name | start_date | deadline | actual_end_date | budget | amount_spent | status | budget_utilization_pct | is_overdue
PRJ2000 | Analytics Dashboard - Grand | Grand Works | 2023-11-26 | 2024-07-17 |  | 659208.02 | 37616.17 | Cancelled | 5.71 | FALSE
PRJ2001 | POS System - Swift | Swift Solutions | 2024-05-14 | 2024-07-29 | 2024-07-29 | 2192490.59 | 1609119.71 | Completed | 73.39 | FALSE
PRJ2002 | Mobile App - Tech | Tech Works | 2022-07-20 | 2022-08-31 |  | 1374440.45 | 151642.7 | In Progress | 11.03 | TRUE
PRJ2003 | Website Redesign - Cloud | Cloud Net | 2023-04-30 | 2023-07-11 | 2023-07-26 | 573680.88 | 505107.73 | Completed | 88.05 | FALSE
PRJ2004 | E-commerce Platform - Quantum | Quantum Works | 2024-02-16 | 2024-03-17 | 2024-04-12 | 2319969.28 | 2443642.69 | Delayed | 105.33 | TRUE
PRJ2005 | Website Redesign - Crest | Crest Systems | 2025-02-12 | 2025-08-30 |  | 429252.22 | 132078.97 | Completed | 30.77 | FALSE
PRJ2006 | Payment Gateway - Swift | Swift Industries | 2025-01-15 | 2025-03-01 |  | 190054.92 | 96723.57 | On Hold | 50.89 | TRUE
PRJ2007 | Mobile App - Nova | Nova Net | 2022-11-19 | 2023-01-02 | 2023-01-17 | 2135789.24 | 1560908.67 | Delayed | 73.08 | TRUE
PRJ2008 | Cloud Migration - Grand | Grand Net | 2023-04-27 | 2023-09-07 | 2023-09-28 | 653227.6 | 632019.66 | Completed | 96.75 | FALSE
PRJ2009 | CRM Integration - Apex | Apex Corp | 2024-05-08 | 2024-11-22 |  | 1330817.65 | 1003828.27 | In Progress | 75.43 | TRUE
PRJ2010 | Inventory Management - Apex | Apex Industries | 2023-10-06 | 2024-01-05 | 2023-12-29 | 1118340.91 | 1415858.05 | Completed | 126.6 | FALSE
PRJ2011 | CRM Integration - Cloud | Cloud Net | 2022-05-29 | 2022-06-30 | 2022-07-21 | 2490436.3 | 1825408.43 | Completed | 73.3 | FALSE
PRJ2012 | ERP System - Vivid | Vivid Works | 2023-06-28 | 2023-08-30 | 2023-09-13 | 2204212.09 | 1909480.7 | Delayed | 86.63 | TRUE
PRJ2013 | Payment Gateway - Cloud | Cloud Group | 2025-01-17 | 2025-08-15 | 2025-09-10 | 1345904.7 | 1346629.39 | Completed | 100.05 | FALSE
PRJ2014 | Marketing Website - Grand | Grand Group | 2025-09-20 | 2025-11-15 | 2025-12-03 | 697941.51 | 767994.4 | Delayed | 110.04 | TRUE
PRJ2015 | API Development - Tech | Tech Works | 2022-11-15 | 2023-02-22 | 2023-02-20 | 1808149.86 | 0 | Completed | 0 | FALSE
PRJ2016 | E-commerce Platform - Vivid | Vivid Industries | 2024-11-01 | 2025-04-05 | 2025-03-24 | 276131.25 | 245925 | Completed | 89.06 | FALSE
PRJ2017 | Marketing Website - Pixel | Pixel Works | 2022-01-08 | 2022-05-03 |  | 1610927.77 | 456486.48 | On Hold | 28.34 | TRUE
PRJ2018 | Marketing Website - Cloud | Cloud Group | 2025-02-03 | 2025-09-01 | 2025-08-17 | 324091.01 | 364690.84 | Completed | 112.53 | FALSE
PRJ2019 | ERP System - Nova | Nova Systems | 2025-01-22 | 2025-03-02 |  | 1477148.44 | 65626.95 | Cancelled | 4.44 | FALSE
PRJ2020 | Inventory Management - Pixel | Pixel Works | 2023-09-24 | 2024-01-25 | 2024-03-25 | 2431880.85 | 1745975.41 | Delayed | 71.8 | TRUE
PRJ2021 | Cloud Migration - Quantum | Quantum Corp | 2023-05-27 | 2023-12-13 | 2024-01-02 | 2216130.02 | 1956554.32 | Completed | 88.29 | FALSE
PRJ2022 | HRMS Portal - Bright | Bright Enterprises | 2023-01-15 | 2023-02-11 |  | 2441704.78 | 593899.56 | Cancelled | 24.32 | FALSE
PRJ2023 | POS System - Grand | Grand Enterprises | 2022-02-20 | 2022-05-06 |  | 863854.4 | 649248.02 | On Hold | 75.16 | TRUE
PRJ2024 | LMS Platform - Apex | Apex Industries | 2023-05-24 | 2023-08-30 | 2023-09-28 | 314834.28 | 343948.6 | Completed | 109.25 | FALSE
PRJ2025 | POS System - Pixel | Pixel Net | 2023-04-01 | 2023-06-21 |  | 1177742.92 | 107830.91 | Cancelled | 9.16 | FALSE
PRJ2026 | Mobile App - Crest | Crest Group | 2023-04-02 | 2023-05-08 |  | 1026241.65 | 302764.01 | In Progress | 29.5 | TRUE
PRJ2027 | Payment Gateway - Grand | Grand Technologies | 2023-07-26 | 2023-11-22 |  | 1029212.04 | 809788.95 | In Progress | 78.68 | TRUE
PRJ2028 | E-commerce Platform - Bright | Bright Works | 2022-02-26 | 2022-04-26 |  | 689977.23 | 120178.11 | Cancelled | 17.42 | FALSE
PRJ2029 | Mobile App - Pixel | Pixel Works | 2022-08-11 | 2023-02-09 | 2023-02-14 | 1119165.02 | 1279100.56 | Completed | 114.29 | FALSE
PRJ2030 | POS System - Swift | Swift Systems | 2025-03-26 | 2025-06-12 | 2025-07-12 | 1118340.91 | 1044490.33 | Completed | 93.4 | FALSE
PRJ2031 | API Development - Quantum | Quantum Industries | 2023-02-08 | 2023-06-11 | 2023-07-08 | 2305888.6 | 2260739.15 | Completed | 98.04 | FALSE
PRJ2032 | Payment Gateway - Tech | Tech Hub | 2023-09-08 | 2024-02-14 | 2024-02-25 | 849148.12 | 860818.63 | Completed | 101.37 | FALSE
PRJ2033 | ERP System - Swift | Swift Solutions | 2023-01-28 | 2023-06-14 |  | 978905.93 | 610537.94 | In Progress | 62.37 | TRUE
PRJ2034 | POS System - Silver | Silver Ventures | 2025-03-11 | 2025-06-26 | 2025-06-11 | 794493.63 | 631290.5 | Completed | 79.46 | FALSE
PRJ2035 | Analytics Dashboard - Swift | Swift Industries | 2025-05-27 | 2025-12-10 | 2025-12-23 | 1133291.51 | 902287.75 | Completed | 79.62 | FALSE
PRJ2036 | Mobile App - Bright | Bright Enterprises | 2022-12-14 | 2023-06-30 | 2023-07-17 | 1676441.9 | 1640678.97 | Completed | 97.87 | FALSE
PRJ2037 | Analytics Dashboard - Cloud | Cloud Net | 2023-04-27 | 2023-11-15 | 2023-11-12 | 411017.21 | 296259.63 | Completed | 72.08 | FALSE
PRJ2038 | Booking System - Silver | Silver Ventures | 2022-05-30 | 2022-10-23 | 2022-11-17 | 1460393.7 | 1494356.12 | Completed | 102.33 | FALSE
PRJ2039 | POS System - Vivid | Vivid Ventures | 2024-03-29 | 2024-06-29 | 2024-07-28 | 63584.8 | 65996.83 | Completed | 103.79 | FALSE
PRJ2040 | CRM Integration - Cloud | Cloud Technologies | 2024-05-20 | 2024-08-14 | 2024-09-12 | 1318996.49 | 953104.59 | Completed | 72.26 | FALSE
PRJ2041 | Cloud Migration - Tech | Tech Hub | 2024-07-23 | 2024-09-25 |  | 1685565.44 | 499547.21 | Cancelled | 29.64 | FALSE
PRJ2042 | HRMS Portal - Urban | Urban Industries | 2024-06-25 | 2024-12-28 |  | 2235449.73 | 286187.25 | Cancelled | 12.8 | FALSE
PRJ2043 | CRM Integration - Tech | Tech Works | 2024-07-02 | 2024-09-10 |  | 1212952.37 | 341366.14 | On Hold | 28.14 | TRUE
PRJ2044 | Analytics Dashboard - Bright | Bright Ventures | 2023-07-22 | 2024-03-04 |  | 1237262.69 | 330933.26 | On Hold | 26.75 | TRUE
PRJ2045 | ERP System - Grand | Grand Systems | 2023-08-09 | 2023-11-07 | 2023-11-12 | 2237915.74 | 1647687.72 | Completed | 73.63 | FALSE
PRJ2046 | Payment Gateway - Crest | Crest Group | 2024-02-24 | 2024-09-18 | 2024-09-16 | 207360.68 | 183186.51 | Completed | 88.34 | FALSE
PRJ2047 | Marketing Website - Tech | Tech Technologies | 2024-05-01 | 2024-06-15 | 2024-06-26 | 1004218.19 | 1050822.05 | Completed | 104.64 | FALSE
PRJ2048 | HRMS Portal - Nova | Nova Corp | 2025-03-25 | 2025-07-30 | 2025-08-06 | 781601 | 684286.98 | Completed | 87.55 | FALSE
PRJ2049 | Analytics Dashboard - Grand | Grand Enterprises | 2025-01-07 | 2025-08-16 |  | 2009677.02 | 1463985.29 | On Hold | 72.85 | TRUE
PRJ2050 | Booking System - Crest | Crest Group | 2023-07-13 | 2023-12-01 | 2023-12-10 | 873517.38 | 878421.17 | Completed | 100.56 | FALSE
PRJ2051 | Cloud Migration - Grand | Grand Works | 2022-12-05 | 2023-05-03 | 2023-06-21 | 1358602.89 | 1505492.3 | Delayed | 110.81 | TRUE
PRJ2052 | Website Redesign - Silver | Silver Systems | 2025-09-19 | 2025-10-25 | 2025-11-06 | 382463.74 | 347186.93 | Completed | 90.78 | FALSE
PRJ2053 | E-commerce Platform - Vivid | Vivid Industries | 2024-02-16 | 2024-06-08 | 2024-06-13 | 876876.34 | 960914.41 | Completed | 109.58 | FALSE
PRJ2054 | Website Redesign - Cloud | Cloud Net | 2024-05-13 | 2024-08-15 |  | 1202251.75 | 270154.72 | Cancelled | 22.47 | FALSE
PRJ2055 | CRM Integration - Royal | Royal Ventures | 2023-04-05 | 2023-10-18 | 2023-11-13 | 148632.44 | 106118.14 | Completed | 71.4 | FALSE
PRJ2056 | CRM Integration - Nova | Nova Technologies | 2022-02-11 | 2022-08-19 | 2022-08-12 | 1210224.6 | 909453.83 | Completed | 75.15 | FALSE
PRJ2057 | Mobile App - Tech | Tech Technologies | 2023-06-09 | 2024-01-21 | 2024-02-13 | 1537756.36 | 1593986.79 | Completed | 103.66 | FALSE
PRJ2058 | HRMS Portal - Grand | Grand Technologies | 2022-12-02 | 2023-03-21 | 2023-03-07 | 2325773.56 | 2230669.26 | Completed | 95.91 | FALSE
PRJ2059 | Mobile App - Swift | Swift Systems | 2024-03-23 | 2024-10-22 | 2024-11-13 | 1742005.32 | 1711100.54 | Completed | 98.23 | FALSE
PRJ2060 | POS System - Vivid | Vivid Net | 2023-09-10 | 2024-04-02 |  | 346584.91 | 273348.42 | In Progress | 78.87 | TRUE
PRJ2061 | Website Redesign - Pixel | Pixel Works | 2023-12-13 | 2024-05-27 | 2024-06-04 | 218944 | 217059.87 | Completed | 99.14 | FALSE
PRJ2062 | Marketing Website - Grand | Grand Enterprises | 2024-09-30 | 2024-11-26 | 2024-12-04 | 1607183.51 | 1724376.58 | Completed | 107.29 | FALSE
PRJ2063 | POS System - Nova | Nova Systems | 2024-06-10 | 2024-08-24 |  | 2415410.64 | 698192.99 | On Hold | 28.91 | TRUE
PRJ2064 | LMS Platform - Quantum | Quantum Industries | 2024-09-17 | 2025-02-13 | 2025-03-07 | 707569.07 | 766489 | Completed | 108.33 | FALSE
PRJ2065 | Inventory Management - Apex | Apex Corp | 2023-07-26 | 2023-12-18 | 2024-01-01 | 1446131.63 | 1447121.96 | Completed | 100.07 | FALSE
PRJ2066 | E-commerce Platform - Nova | Nova Corp | 2024-10-09 | 2025-01-30 | 2025-01-28 | 919321.17 | 750403.8 | Completed | 81.63 | FALSE
PRJ2067 | Analytics Dashboard - Bharat | Bharat Net | 2023-07-20 | 2024-01-08 | 2024-01-05 | 259751.76 | 265994.53 | Completed | 102.4 | FALSE
PRJ2068 | Mobile App - Tech | Tech Works | 2023-05-08 | 2023-11-30 | 2023-12-30 | 1252512.27 | 1323679.75 | Completed | 105.68 | FALSE
PRJ2069 | Analytics Dashboard - Royal | Royal Labs | 2023-03-30 | 2023-08-10 |  | 800204.77 | 405774.96 | In Progress | 50.71 | TRUE
PRJ2070 | E-commerce Platform - Tech | Tech Works | 2024-12-23 | 2025-04-20 | 2025-05-10 | 860438.68 | 874450.69 | Completed | 101.63 | FALSE
PRJ2071 | POS System - Grand | Grand Group | 2023-05-30 | 2023-08-27 | 2023-08-24 | 823092.46 | 851321.63 | Completed | 103.43 | FALSE
PRJ2072 | POS System - Vivid | Vivid Net | 2023-01-15 | 2023-04-04 | 2023-04-19 | 727424.09 | 702192.74 | Completed | 96.53 | FALSE
PRJ2073 | E-commerce Platform - Nova | Nova Net | 2025-05-07 | 2025-08-17 | 2025-09-08 | 775803.83 | 669050.49 | Delayed | 86.24 | TRUE
PRJ2074 | ERP System - Apex | Apex Systems | 2024-12-29 | 2025-03-01 | 2025-02-17 | 1405729.47 | 1425181.71 | Completed | 101.38 | FALSE
PRJ2075 | Analytics Dashboard - Bright | Bright Ventures | 2024-10-02 | 2024-11-27 |  | 1456457.34 | 205096.99 | Cancelled | 14.08 | FALSE
PRJ2076 | Analytics Dashboard - Bright | Bright Works | 2023-01-13 | 2023-02-25 | 2023-03-12 | 329513.49 | 240348.64 | Completed | 72.94 | FALSE
PRJ2077 | E-commerce Platform - Grand | Grand Systems | 2025-03-27 | 2025-10-04 |  | 421731.17 | 281631.84 | In Progress | 66.78 | TRUE
PRJ2078 | Cloud Migration - Apex | Apex Corp | 2023-05-24 | 2023-07-23 |  | 1069626.35 | 553305.72 | In Progress | 51.73 | TRUE
PRJ2079 | Booking System - Crest | Crest Group | 2024-12-06 | 2025-04-12 | 2025-04-25 | 778515.17 | 751139.71 | Completed | 96.48 | FALSE

## Tasks
task_id | project_name | assignee | priority | created_date | completed_date | estimated_hours | actual_hours | task_status | hours_variance
TSK3000 | POS System - Vivid | Tanvi Desai | Medium | 2024-08-21 | 2024-09-30 | 76.9 | 53.8 | Completed | -23.1
TSK3001 | Payment Gateway - Grand | Priya Singh | Low | 2023-10-01 | 2023-10-12 | 20.7 | 23.8 | Completed | 3.1
TSK3002 | Website Redesign - Silver | Siddharth Iyer | High | 2026-01-12 | 2026-02-12 | 24.7 | 20.5 | Completed | -4.2
TSK3003 | HRMS Portal - Grand | Pooja Reddy | Medium | 2022-12-20 | 2023-01-06 | 63.5 | 77.8 | Completed | 14.3
TSK3004 | Website Redesign - Cloud | Priya Singh | Low | 2024-06-11 | 2024-07-23 | 13.6 | 11.8 | Completed | -1.8
TSK3005 | Mobile App - Nova | Isha Bansal | High | 2022-12-31 |  | 48.4 | 35.9 | Open | -12.5
TSK3006 | CRM Integration - Nova | Neha Kapoor | Critical | 2022-03-14 | 2022-04-03 | 56.6 | 87.3 | Completed | 30.7
TSK3007 | CRM Integration - Nova | Riya Sharma | Low | 2022-03-03 | 2022-03-31 | 59.3 | 71.4 | Completed | 12.1
TSK3008 | Mobile App - Pixel | Tanvi Desai | High | 2023-01-30 |  | 37.1 | 40.1 | Open | 3
TSK3009 | E-commerce Platform - Nova | Vikram Joshi | High | 2025-05-17 |  | 15.7 | 7.3 | Open | -8.4
TSK3010 | POS System - Grand | Ananya Rao | High | 2022-07-19 | 2022-08-20 | 77.6 | 83 | Completed | 5.4
TSK3011 | Cloud Migration - Tech | Sneha Patel | Critical | 2025-01-10 | 2025-01-21 | 27.7 | 35.8 | Completed | 8.1
TSK3012 | E-commerce Platform - Tech | Tanvi Desai | Critical | 2025-01-01 | 2025-01-22 | 21.7 | 15.5 | Completed | -6.2
TSK3013 | Inventory Management - Apex | Neha Kapoor | High | 2023-07-26 | 2023-08-30 | 38 | 24.9 | Completed | -13.1
TSK3014 | Booking System - Crest | Neha Kapoor | Medium | 2025-06-17 | 2025-07-16 | 61.3 | 0 | Completed | -61.3
TSK3015 | Mobile App - Bright | Pooja Reddy | Medium | 2023-04-05 |  | 39.8 | 1 | Open | -38.8
TSK3016 | Inventory Management - Pixel | Manish Kumar | Low | 2023-12-12 | 2024-01-17 | 33.8 | 27.9 | Completed | -5.9
TSK3017 | Mobile App - Swift | Neha Kapoor | High | 2024-04-22 | 2024-05-02 | 40.9 | 53.8 | Completed | 12.9
TSK3018 | E-commerce Platform - Vivid | Ananya Rao | Medium | 2024-06-18 |  | 21 | 10.4 | Open | -10.6
TSK3019 | Analytics Dashboard - Bright | Tanvi Desai | Critical | 2023-05-23 | 2023-06-01 | 69.4 | 60.8 | Completed | -8.6
TSK3020 | CRM Integration - Tech | Arjun Nair | Critical | 2024-11-08 | 2024-11-09 | 24.1 | 21.7 | Completed | -2.4
TSK3021 | ERP System - Nova | Ananya Rao | Critical | 2025-05-16 | 2025-06-08 | 27.9 | 38 | Completed | 10.1
TSK3022 | Cloud Migration - Tech | Manish Kumar | Critical | 2024-09-09 |  | 20.6 | 7.1 | Open | -13.5
TSK3023 | Website Redesign - Crest | Manish Kumar | Medium | 2025-05-04 | 2025-05-29 | 32.1 | 40.6 | Completed | 8.5
TSK3024 | POS System - Nova | Manish Kumar | Critical | 2024-06-19 | 2024-07-27 | 27.9 | 19.5 | Completed | -8.4
TSK3025 | ERP System - Vivid | Manish Kumar | Medium | 2023-11-09 |  | 3.2 | 0.4 | Open | -2.8
TSK3026 | CRM Integration - Apex | Ananya Rao | Low | 2024-09-05 |  | 22.7 | 12.7 | Open | -10
TSK3027 | HRMS Portal - Urban | Siddharth Iyer | Critical | 2024-12-14 |  | 31.6 | 9 | Open | -22.6
TSK3028 | Analytics Dashboard - Royal | Karan Mehta | Low | 2023-04-08 | 2023-04-24 | 51.2 | 77.9 | Completed | 26.7
TSK3029 | CRM Integration - Royal | Priya Singh | High | 2023-04-30 |  | 56.9 | 5.1 | Open | -51.8
TSK3030 | Website Redesign - Cloud | Priya Singh | Medium | 2023-05-11 | 2023-05-15 | 24.9 | 24.3 | Completed | -0.6
TSK3031 | Analytics Dashboard - Bharat | Manish Kumar | Critical | 2023-11-02 | 2023-11-14 | 15.3 | 10.4 | Completed | -4.9
TSK3032 | Booking System - Crest | Sneha Patel | Critical | 2025-05-29 | 2025-07-06 | 13.2 | 14 | Completed | 0.8
TSK3033 | Payment Gateway - Tech | Priya Singh | Low | 2024-02-25 | 2024-03-26 | 72.3 | 92.4 | Completed | 20.1
TSK3034 | CRM Integration - Nova | Siddharth Iyer | High | 2022-05-10 |  | 25.3 | 21.9 | Open | -3.4
TSK3035 | HRMS Portal - Grand | Ananya Rao | High | 2023-02-17 | 2023-03-14 | 68.6 | 48.5 | Completed | -20.1
TSK3036 | E-commerce Platform - Nova | Pooja Reddy | Critical | 2025-07-21 |  | 25 | 22 | Open | -3
TSK3037 | Analytics Dashboard - Swift | Isha Bansal | Critical | 2025-05-29 | 2025-07-12 | 62.7 | 98.7 | Completed | 36
TSK3038 | Mobile App - Bright | Pooja Reddy | Medium | 2023-06-30 |  | 49.4 | 15.7 | Open | -33.7
TSK3039 | Booking System - Crest | Aman Verma | Low | 2025-02-08 | 2025-03-23 | 55.1 | 40.6 | Completed | -14.5
TSK3040 | POS System - Vivid | Sneha Patel | High | 2024-07-19 | 2024-08-12 | 59.1 | 40.8 | Completed | -18.3
TSK3041 | E-commerce Platform - Vivid | Neha Kapoor | High | 2024-03-31 | 2024-05-05 | 70.4 | 68 | Completed | -2.4
TSK3042 | Cloud Migration - Quantum | Sneha Patel | High | 2023-07-31 |  | 75.6 | 65.8 | Open | -9.8
TSK3043 | Marketing Website - Grand | Manish Kumar | Critical | 2026-01-17 |  | 13 | 11.3 | Open | -1.7
TSK3044 | POS System - Grand | Vikram Joshi | High | 2023-08-31 | 2023-09-26 | 3.1 | 3.5 | Completed | 0.4
TSK3045 | ERP System - Swift | Karan Mehta | Critical | 2023-06-26 | 2023-08-06 | 75.3 | 53.3 | Completed | -22
TSK3046 | Website Redesign - Cloud | Karan Mehta | Low | 2023-10-05 |  | 45.8 | 37.7 | Open | -8.1
TSK3047 | Mobile App - Swift | Riya Sharma | High | 2024-09-18 | 2024-10-15 | 11.1 | 7.2 | Completed | -3.9
TSK3048 | POS System - Nova | Pooja Reddy | Critical | 2024-07-09 | 2024-08-13 | 12.6 | 13.3 | Completed | 0.7
TSK3049 | Analytics Dashboard - Bright | Arjun Nair | Critical | 2025-04-10 | 2025-05-07 | 53.1 | 76.1 | Completed | 23
TSK3050 | Analytics Dashboard - Swift | Manish Kumar | High | 2025-06-04 | 2025-06-18 | 36.6 | 56.8 | Completed | 20.2
TSK3051 | ERP System - Vivid | Karan Mehta | Low | 2023-12-20 | 2024-01-31 | 30 | 29.9 | Completed | -0.1
TSK3052 | HRMS Portal - Grand | Riya Sharma | High | 2022-12-25 | 2023-02-05 | 51.9 | 81.5 | Completed | 29.6
TSK3053 | API Development - Quantum | Neha Kapoor | Medium | 2023-03-12 |  | 18 | 13.4 | Open | -4.6
TSK3054 | Analytics Dashboard - Bright | Tanvi Desai | Low | 2024-11-26 |  | 20.2 | 14.1 | Open | -6.1
TSK3055 | Analytics Dashboard - Swift | Aman Verma | Low | 2023-05-10 |  | 44.1 | 31.7 | Open | -12.4
TSK3056 | E-commerce Platform - Vivid | Sneha Patel | Low | 2024-11-04 | 2024-11-20 | 47.9 | 29.5 | Completed | -18.4
TSK3057 | E-commerce Platform - Vivid | Tanvi Desai | High | 2025-05-09 | 2025-05-17 | 60.2 | 64.8 | Completed | 4.6
TSK3058 | Inventory Management - Apex | Siddharth Iyer | High | 2023-12-24 | 2024-01-26 | 19.3 | 23.5 | Completed | 4.2
TSK3059 | HRMS Portal - Grand | Ananya Rao | Critical | 2023-05-15 |  | 6.7 | 2.9 | Open | -3.8
TSK3060 | Payment Gateway - Cloud | Arjun Nair | Medium | 2025-05-22 | 2025-06-20 | 7.7 | 5.2 | Completed | -2.5
TSK3061 | Cloud Migration - Grand | Ananya Rao | High | 2023-05-29 | 2023-07-09 | 47.7 | 62.6 | Completed | 14.9
TSK3062 | HRMS Portal - Grand | Pooja Reddy | Medium | 2023-04-10 | 2023-04-17 | 63.9 | 45.7 | Completed | -18.2
TSK3063 | CRM Integration - Royal | Ananya Rao | Critical | 2023-07-29 |  | 34.3 | 25.5 | Open | -8.8
TSK3064 | ERP System - Vivid | Pooja Reddy | Critical | 2023-09-16 | 2023-10-29 | 21.9 | 34 | Completed | 12.1
TSK3065 | Cloud Migration - Grand | Siddharth Iyer | High | 2023-05-20 |  | 9.3 | 0.8 | Open | -8.5
TSK3066 | E-commerce Platform - Vivid | Ananya Rao | High | 2025-03-23 | 2025-04-28 | 45.8 | 58.2 | Completed | 12.4
TSK3067 | Website Redesign - Cloud | Arjun Nair | Medium | 2024-11-13 | 2024-12-02 | 48.8 | 46.4 | Completed | -2.4
TSK3068 | ERP System - Nova | Aman Verma | High | 2025-07-09 | 2025-07-16 | 29.3 | 33.9 | Completed | 4.6
TSK3069 | E-commerce Platform - Nova | Manish Kumar | Low | 2025-07-03 |  | 67.9 | 59.6 | Open | -8.3
TSK3070 | E-commerce Platform - Grand | Siddharth Iyer | High | 2025-09-11 |  | 22.9 | 3.7 | Open | -19.2
TSK3071 | CRM Integration - Tech | Priya Singh | Low | 2024-09-29 | 2024-10-09 | 46.2 | 46.2 | Completed | 0
TSK3072 | CRM Integration - Cloud | Rohan Gupta | High | 2022-12-06 | 2022-12-31 | 34.7 | 32.6 | Completed | -2.1
TSK3073 | Cloud Migration - Tech | Priya Singh | Medium | 2025-02-06 |  | 48.5 | 38.6 | Open | -9.9
TSK3074 | Booking System - Crest | Arjun Nair | Critical | 2024-12-18 | 2025-01-05 | 36.6 | 37.5 | Completed | 0.9
TSK3075 | E-commerce Platform - Vivid | Sneha Patel | Critical | 2024-04-25 | 2024-05-28 | 10.9 | 11.2 | Completed | 0.3
TSK3076 | Analytics Dashboard - Bharat | Riya Sharma | Medium | 2024-01-06 | 2024-01-21 | 32.8 | 39.3 | Completed | 6.5
TSK3077 | Booking System - Silver | Aman Verma | Low | 2022-07-23 |  | 61.6 | 16 | Open | -45.6
TSK3078 | POS System - Nova | Neha Kapoor | High | 2024-12-18 | 2024-12-27 | 31.7 | 41.3 | Completed | 9.6
TSK3079 | CRM Integration - Apex | Isha Bansal | Low | 2024-08-17 |  | 5.3 | 0.1 | Open | -5.2
TSK3080 | CRM Integration - Cloud | Aman Verma | Critical | 2024-10-14 | 2024-11-09 | 57.3 | 58.3 | Completed | 1
TSK3081 | Mobile App - Tech | Rohan Gupta | Low | 2022-10-11 | 2022-11-20 | 37.9 | 48.9 | Completed | 11
TSK3082 | CRM Integration - Royal | Manish Kumar | High | 2023-05-02 | 2023-06-09 | 33.2 | 22.5 | Completed | -10.7
TSK3083 | CRM Integration - Tech | Neha Kapoor | Medium | 2024-08-27 | 2024-09-07 | 8 | 9.9 | Completed | 1.9
TSK3084 | Analytics Dashboard - Bright | Priya Singh | High | 2023-10-19 | 2023-11-30 | 65.6 | 54.9 | Completed | -10.7
TSK3085 | POS System - Pixel | Pooja Reddy | Critical | 2023-05-15 | 2023-06-26 | 7.9 | 12.3 | Completed | 4.4
TSK3086 | Mobile App - Swift | Arjun Nair | High | 2024-10-02 | 2024-11-09 | 37 | 56.4 | Completed | 19.4
TSK3087 | CRM Integration - Cloud | Sneha Patel | Low | 2024-06-27 | 2024-07-28 | 36.5 | 33 | Completed | -3.5
TSK3088 | ERP System - Grand | Manish Kumar | High | 2023-12-16 | 2024-01-15 | 37.2 | 24.4 | Completed | -12.8
TSK3089 | CRM Integration - Apex | Neha Kapoor | Critical | 2024-10-20 |  | 68.7 | 38 | Open | -30.7
TSK3090 | Mobile App - Swift | Pooja Reddy | Medium | 2024-08-18 | 2024-08-21 | 37.1 | 52.3 | Completed | 15.2
TSK3091 | Cloud Migration - Tech | Tanvi Desai | High | 2024-12-24 | 2025-01-03 | 76.7 | 80.6 | Completed | 3.9
TSK3092 | Inventory Management - Apex | Vikram Joshi | Medium | 2024-02-12 | 2024-02-15 | 21.3 | 22.1 | Completed | 0.8
TSK3093 | Payment Gateway - Crest | Pooja Reddy | Low | 2024-05-29 |  | 32.2 | 22.4 | Open | -9.8
TSK3094 | HRMS Portal - Urban | Siddharth Iyer | Medium | 2024-07-11 | 2024-08-16 | 54.9 | 48.5 | Completed | -6.4
TSK3095 | HRMS Portal - Urban | Pooja Reddy | Critical | 2024-07-15 | 2024-07-25 | 73.5 | 66.9 | Completed | -6.6
TSK3096 | E-commerce Platform - Vivid | Tanvi Desai | High | 2025-04-02 | 2025-04-08 | 26.1 | 25.5 | Completed | -0.6
TSK3097 | E-commerce Platform - Vivid | Pooja Reddy | Critical | 2025-04-21 | 2025-06-04 | 73.2 | 50.8 | Completed | -22.4
TSK3098 | Inventory Management - Apex | Tanvi Desai | Critical | 2023-10-26 | 2023-11-15 | 16.1 | 13.1 | Completed | -3
TSK3099 | LMS Platform - Apex | Tanvi Desai | Low | 2023-07-20 |  | 14.1 | 3.8 | Open | -10.3
TSK3100 | LMS Platform - Quantum | Tanvi Desai | Medium | 2025-04-02 | 2025-05-06 | 4.9 | 4.6 | Completed | -0.3
TSK3101 | Analytics Dashboard - Bright | Tanvi Desai | Medium | 2023-04-19 | 2023-05-01 | 66.8 | 91.6 | Completed | 24.8
TSK3102 | CRM Integration - Nova | Arjun Nair | High | 2022-02-22 | 2022-04-07 | 58.1 | 91.2 | Completed | 33.1
TSK3103 | Mobile App - Tech | Isha Bansal | Medium | 2023-08-07 | 2023-08-27 | 77.3 | 107 | Completed | 29.7
TSK3104 | Marketing Website - Tech | Sneha Patel | Critical | 2024-10-21 |  | 78.8 | 32.7 | Open | -46.1
TSK3105 | LMS Platform - Quantum | Priya Singh | High | 2025-01-30 | 2025-02-10 | 65.7 | 92.1 | Completed | 26.4
TSK3106 | Payment Gateway - Swift | Manish Kumar | Low | 2025-06-28 | 2025-07-22 | 45.3 | 31.8 | Completed | -13.5
TSK3107 | Mobile App - Bright | Priya Singh | Critical | 2023-01-04 |  | 23.3 | 19 | Open | -4.3
TSK3108 | CRM Integration - Cloud | Ananya Rao | Low | 2022-07-24 |  | 71 | 59.5 | Open | -11.5
TSK3109 | Booking System - Crest | Riya Sharma | High | 2023-11-18 | 2023-12-13 | 79.6 | 77.6 | Completed | -2
TSK3110 | ERP System - Vivid | Manish Kumar | Critical | 2023-12-27 | 2024-01-06 | 12.7 | 11.3 | Completed | -1.4
TSK3111 | Marketing Website - Pixel | Riya Sharma | High | 2022-07-21 | 2022-08-19 | 50 | 75.3 | Completed | 25.3
TSK3112 | Payment Gateway - Grand | Sneha Patel | Medium | 2023-09-02 | 2023-10-11 | 43.2 | 30.7 | Completed | -12.5
TSK3113 | Booking System - Silver | Aman Verma | Low | 2022-06-30 | 2022-07-27 | 51.8 | 63.3 | Completed | 11.5
TSK3114 | POS System - Nova | Priya Singh | High | 2024-11-09 | 2024-12-20 | 42.2 | 35.5 | Completed | -6.7
TSK3115 | Website Redesign - Cloud | Pooja Reddy | Low | 2024-05-13 | 2024-05-29 | 46.5 | 36.6 | Completed | -9.9
TSK3116 | Analytics Dashboard - Bharat | Neha Kapoor | Low | 2023-10-20 | 2023-11-23 | 44.4 | 61.6 | Completed | 17.2
TSK3117 | Analytics Dashboard - Grand | Riya Sharma | High | 2025-05-07 | 2025-06-01 | 78.5 | 67 | Completed | -11.5
TSK3118 | Cloud Migration - Grand | Siddharth Iyer | High | 2023-07-24 | 2023-09-05 | 51 | 69.9 | Completed | 18.9
TSK3119 | Marketing Website - Pixel | Tanvi Desai | Critical | 2022-01-19 | 2022-02-10 | 65.5 | 50.8 | Completed | -14.7
TSK3120 | Website Redesign - Pixel | Vikram Joshi | Low | 2024-05-22 | 2024-05-31 | 6.9 | 9.5 | Completed | 2.6
TSK3121 | Analytics Dashboard - Cloud | Sneha Patel | Critical | 2023-06-17 | 2023-06-30 | 71.1 | 65.1 | Completed | -6
TSK3122 | Analytics Dashboard - Royal | Tanvi Desai | Low | 2023-07-29 | 2023-09-09 | 16.9 | 16.2 | Completed | -0.7
TSK3123 | HRMS Portal - Urban | Vikram Joshi | Critical | 2024-09-02 | 2024-09-26 | 36.1 | 36.1 | Completed | 0
TSK3124 | CRM Integration - Tech | Sneha Patel | Low | 2024-08-18 | 2024-09-19 | 30.7 | 42.9 | Completed | 12.2
TSK3125 | Website Redesign - Cloud | Aman Verma | High | 2024-06-02 | 2024-06-14 | 44.5 | 41 | Completed | -3.5
TSK3126 | Analytics Dashboard - Cloud | Vikram Joshi | Low | 2023-07-14 | 2023-08-11 | 15 | 15.7 | Completed | 0.7
TSK3127 | ERP System - Grand | Riya Sharma | Low | 2024-01-13 |  | 23.4 | 20.6 | Open | -2.8
TSK3128 | Cloud Migration - Grand | Manish Kumar | Critical | 2023-03-08 | 2023-04-21 | 14.5 | 9.2 | Completed | -5.3
TSK3129 | E-commerce Platform - Quantum | Arjun Nair | Low | 2024-03-19 | 2024-04-30 | 30.6 | 30.1 | Completed | -0.5
TSK3130 | E-commerce Platform - Grand | Arjun Nair | Medium | 2025-05-05 | 2025-05-29 | 31 | 42.3 | Completed | 11.3
TSK3131 | Analytics Dashboard - Bharat | Riya Sharma | Medium | 2023-10-21 | 2023-12-02 | 23.7 | 37 | Completed | 13.3
TSK3132 | POS System - Nova | Siddharth Iyer | Critical | 2024-10-20 | 2024-11-25 | 11.2 | 15.4 | Completed | 4.2
TSK3133 | Payment Gateway - Grand | Aman Verma | Critical | 2023-12-29 | 2024-01-30 | 17.6 | 12.9 | Completed | -4.7
TSK3134 | HRMS Portal - Bright | Rohan Gupta | High | 2023-07-16 | 2023-07-22 | 65.2 | 102.2 | Completed | 37
TSK3135 | Cloud Migration - Grand | Isha Bansal | Medium | 2023-09-14 | 2023-10-04 | 68.4 | 89.7 | Completed | 21.3
TSK3136 | Payment Gateway - Crest | Vikram Joshi | Low | 2024-07-03 | 2024-07-16 | 63.8 | 53.4 | Completed | -10.4
TSK3137 | Payment Gateway - Crest | Arjun Nair | Low | 2024-07-14 | 2024-08-13 | 64.7 | 74.5 | Completed | 9.8
TSK3138 | Cloud Migration - Grand | Manish Kumar | Low | 2023-07-15 | 2023-08-15 | 43 | 58.9 | Completed | 15.9
TSK3139 | E-commerce Platform - Vivid | Priya Singh | Medium | 2025-01-21 | 2025-02-19 | 38.3 | 42.8 | Completed | 4.5
TSK3140 | E-commerce Platform - Vivid | Sneha Patel | Medium | 2025-02-19 | 2025-02-23 | 66.8 | 74.7 | Completed | 7.9
TSK3141 | Inventory Management - Pixel | Neha Kapoor | High | 2023-12-15 |  | 19.6 | 16.7 | Open | -2.9
TSK3142 | Inventory Management - Apex | Arjun Nair | Low | 2023-12-09 | 2024-01-14 | 23.4 | 28.7 | Completed | 5.3
TSK3143 | LMS Platform - Quantum | Siddharth Iyer | High | 2025-02-28 | 2025-04-07 | 14 | 17.6 | Completed | 3.6
TSK3144 | POS System - Vivid | Pooja Reddy | High | 2023-01-25 |  | 4.2 | 0.2 | Open | -4
TSK3145 | Mobile App - Crest | Pooja Reddy | High | 2023-10-15 | 2023-11-24 | 51.8 | 56.9 | Completed | 5.1
TSK3146 | Booking System - Silver | Siddharth Iyer | Low | 2022-09-30 | 2022-11-13 | 33.7 | 35.5 | Completed | 1.8
TSK3147 | Inventory Management - Pixel | Rohan Gupta | High | 2024-01-14 | 2024-02-13 | 17.9 | 21.6 | Completed | 3.7
TSK3148 | Analytics Dashboard - Bright | Karan Mehta | Critical | 2023-11-01 | 2023-11-25 | 42.2 | 29.8 | Completed | -12.4
TSK3149 | API Development - Tech | Ananya Rao | Critical | 2023-01-22 | 2023-02-01 | 9.6 | 8.5 | Completed | -1.1
TSK3150 | API Development - Quantum | Karan Mehta | Medium | 2023-03-20 |  | 74.8 | 48.5 | Open | -26.3
TSK3151 | POS System - Nova | Ananya Rao | Critical | 2024-10-19 | 2024-11-08 | 40.8 | 28.2 | Completed | -12.6
TSK3152 | POS System - Swift | Isha Bansal | Critical | 2025-05-20 | 2025-05-24 | 5.9 | 6.5 | Completed | 0.6
TSK3153 | Mobile App - Bright | Siddharth Iyer | High | 2023-04-30 | 2023-05-07 | 35.6 | 52.8 | Completed | 17.2
TSK3154 | Cloud Migration - Grand | Neha Kapoor | High | 2023-03-08 | 2023-03-12 | 46.5 | 37 | Completed | -9.5
TSK3155 | CRM Integration - Apex | Pooja Reddy | Low | 2024-08-14 | 2024-09-19 | 23.8 | 37.8 | Completed | 14
TSK3156 | E-commerce Platform - Vivid | Priya Singh | Medium | 2024-11-25 | 2024-12-17 | 45.5 | 43.9 | Completed | -1.6
TSK3157 | E-commerce Platform - Grand | Rohan Gupta | Critical | 2025-08-04 | 2025-08-07 | 5.5 | 4.1 | Completed | -1.4
TSK3158 | E-commerce Platform - Nova | Rohan Gupta | Medium | 2025-02-02 | 2025-03-07 | 12.9 | 19.8 | Completed | 6.9
TSK3159 | Booking System - Crest | Neha Kapoor | Critical | 2023-12-17 | 2024-01-06 | 48.3 | 53.5 | Completed | 5.2
TSK3160 | POS System - Vivid | Ananya Rao | High | 2023-04-01 | 2023-04-03 | 30.7 | 39.1 | Completed | 8.4
TSK3161 | Website Redesign - Cloud | Arjun Nair | Medium | 2023-09-29 | 2023-11-10 | 63.1 | 86.8 | Completed | 23.7
TSK3162 | Payment Gateway - Swift | Manish Kumar | Critical | 2025-06-13 | 2025-07-17 | 51.1 | 62.3 | Completed | 11.2
TSK3163 | Marketing Website - Cloud | Riya Sharma | Critical | 2025-07-27 | 2025-09-02 | 76 | 54 | Completed | -22
TSK3164 | CRM Integration - Cloud | Arjun Nair | Critical | 2024-09-04 | 2024-10-19 | 17.9 | 19.7 | Completed | 1.8
TSK3165 | Mobile App - Nova | Vikram Joshi | Critical | 2023-05-18 | 2023-06-01 | 45.7 | 73 | Completed | 27.3
TSK3166 | CRM Integration - Cloud | Tanvi Desai | High | 2024-07-03 | 2024-08-07 | 28.7 | 27.4 | Completed | -1.3
TSK3167 | Cloud Migration - Apex | Sneha Patel | High | 2023-09-24 | 2023-10-10 | 23.8 | 21.4 | Completed | -2.4
TSK3168 | Mobile App - Crest | Isha Bansal | High | 2023-09-25 | 2023-10-16 | 39.4 | 45.7 | Completed | 6.3
TSK3169 | Mobile App - Bright | Manish Kumar | High | 2023-01-14 | 2023-02-18 | 31.6 | 49.9 | Completed | 18.3
TSK3170 | Marketing Website - Cloud | Sneha Patel | Critical | 2025-04-18 | 2025-04-24 | 29 | 30.2 | Completed | 1.2
TSK3171 | Payment Gateway - Grand | Sneha Patel | Medium | 2023-09-15 |  | 23.1 | 11.7 | Open | -11.4
TSK3172 | Payment Gateway - Cloud | Neha Kapoor | Medium | 2025-06-23 | 2025-07-09 | 20.9 | 26.5 | Completed | 5.6
TSK3173 | Mobile App - Pixel | Tanvi Desai | Medium | 2022-08-24 | 2022-09-15 | 58 | 40.6 | Completed | -17.4
TSK3174 | Analytics Dashboard - Grand | Isha Bansal | Critical | 2024-04-14 |  | 14.3 | 8.4 | Open | -5.9
TSK3175 | Website Redesign - Pixel | Isha Bansal | Low | 2024-05-27 | 2024-06-15 | 27.1 | 33.8 | Completed | 6.7
TSK3176 | E-commerce Platform - Nova | Isha Bansal | Medium | 2025-07-05 | 2025-07-08 | 73.2 | 56.7 | Completed | -16.5
TSK3177 | E-commerce Platform - Quantum | Manish Kumar | High | 2024-05-27 |  | 16.5 | 11.1 | Open | -5.4
TSK3178 | E-commerce Platform - Quantum | Sneha Patel | Critical | 2024-02-18 | 2024-03-28 | 10.4 | 16.5 | Completed | 6.1
TSK3179 | Analytics Dashboard - Royal | Karan Mehta | Low | 2023-08-11 | 2023-08-20 | 68.4 | 73.1 | Completed | 4.7
TSK3180 | HRMS Portal - Urban | Siddharth Iyer | High | 2024-08-05 | 2024-09-16 | 22.1 | 17.4 | Completed | -4.7
TSK3181 | Analytics Dashboard - Cloud | Isha Bansal | Critical | 2023-09-19 | 2023-10-02 | 15.7 | 22.9 | Completed | 7.2
TSK3182 | Website Redesign - Cloud | Priya Singh | Critical | 2024-09-21 | 2024-10-17 | 54.2 | 42.5 | Completed | -11.7
TSK3183 | Cloud Migration - Tech | Rohan Gupta | High | 2024-09-24 | 2024-10-19 | 20.4 | 27.6 | Completed | 7.2
TSK3184 | ERP System - Apex | Riya Sharma | Low | 2025-07-02 | 2025-07-19 | 53 | 68.5 | Completed | 15.5
TSK3185 | Mobile App - Swift | Siddharth Iyer | High | 2024-06-09 | 2024-07-23 | 41.2 | 61.6 | Completed | 20.4
TSK3186 | API Development - Tech | Karan Mehta | Medium | 2023-04-27 |  | 25 | 13.8 | Open | -11.2
TSK3187 | Website Redesign - Pixel | Isha Bansal | Critical | 2024-01-21 | 2024-02-29 | 31.1 | 40.5 | Completed | 9.4
TSK3188 | Mobile App - Tech | Arjun Nair | Low | 2023-10-25 |  | 61.4 | 37.6 | Open | -23.8
TSK3189 | Analytics Dashboard - Bharat | Riya Sharma | Medium | 2023-11-11 | 2023-12-05 | 8.1 | 9.4 | Completed | 1.3
TSK3190 | E-commerce Platform - Nova | Pooja Reddy | Medium | 2025-09-21 | 2025-10-12 | 68.6 | 71.5 | Completed | 2.9
TSK3191 | ERP System - Apex | Priya Singh | Critical | 2025-05-03 | 2025-06-05 | 36.7 | 24.1 | Completed | -12.6
TSK3192 | HRMS Portal - Grand | Riya Sharma | Critical | 2023-04-25 | 2023-05-25 | 54.5 | 49.5 | Completed | -5
TSK3193 | Payment Gateway - Tech | Siddharth Iyer | Low | 2023-09-08 | 2023-10-16 | 7.7 | 7.9 | Completed | 0.2
TSK3194 | Analytics Dashboard - Royal | Riya Sharma | High | 2023-04-14 |  | 7.4 | 6.2 | Open | -1.2
TSK3195 | Website Redesign - Silver | Pooja Reddy | Critical | 2025-11-04 |  | 61.7 | 54.3 | Open | -7.4
TSK3196 | Marketing Website - Tech | Pooja Reddy | Medium | 2024-08-06 | 2024-08-31 | 31.3 | 40.1 | Completed | 8.8
TSK3197 | Analytics Dashboard - Bright | Karan Mehta | Low | 2023-08-21 | 2023-09-25 | 32.7 | 23.8 | Completed | -8.9
TSK3198 | Mobile App - Tech | Karan Mehta | Medium | 2022-10-04 | 2022-11-08 | 35.1 | 34.4 | Completed | -0.7
TSK3199 | HRMS Portal - Grand | Aman Verma | Low | 2023-02-28 | 2023-03-13 | 75.1 | 99.5 | Completed | 24.4
TSK3200 | E-commerce Platform - Vivid | Karan Mehta | Low | 2024-07-22 |  | 70.9 | 1 | Open | -69.9
TSK3201 | ERP System - Vivid | Karan Mehta | Low | 2023-11-27 | 2024-01-05 | 54.4 | 80.1 | Completed | 25.7
TSK3202 | Cloud Migration - Grand | Priya Singh | High | 2023-03-27 | 2023-04-10 | 60.8 | 83.7 | Completed | 22.9
TSK3203 | Mobile App - Pixel | Rohan Gupta | Medium | 2023-02-14 | 2023-03-23 | 48.6 | 61.8 | Completed | 13.2
TSK3204 | Booking System - Silver | Sneha Patel | Low | 2022-07-05 |  | 42.7 | 15.9 | Open | -26.8
TSK3205 | POS System - Grand | Ananya Rao | Critical | 2023-10-28 |  | 73.1 | 41.2 | Open | -31.9
TSK3206 | Payment Gateway - Swift | Rohan Gupta | Critical | 2025-04-13 |  | 54.4 | 38.5 | Open | -15.9
TSK3207 | Website Redesign - Silver | Manish Kumar | Medium | 2025-10-27 | 2025-11-08 | 60.8 | 65.3 | Completed | 4.5
TSK3208 | Booking System - Silver | Ananya Rao | Medium | 2022-11-27 | 2022-12-27 | 73.3 | 85.2 | Completed | 11.9
TSK3209 | Analytics Dashboard - Grand | Manish Kumar | High | 2025-03-10 | 2025-04-01 | 52.4 | 79.8 | Completed | 27.4
TSK3210 | CRM Integration - Cloud | Arjun Nair | Low | 2022-10-13 | 2022-10-26 | 6 | 5.9 | Completed | -0.1
TSK3211 | CRM Integration - Apex | Karan Mehta | Critical | 2024-06-25 |  | 47.8 | 28.9 | Open | -18.9
TSK3212 | Mobile App - Crest | Siddharth Iyer | Low | 2023-06-26 | 2023-06-27 | 18.5 | 14.6 | Completed | -3.9
TSK3213 | Website Redesign - Pixel | Rohan Gupta | High | 2024-02-13 | 2024-02-27 | 32.9 | 27.6 | Completed | -5.3
TSK3214 | HRMS Portal - Nova | Isha Bansal | Critical | 2025-07-22 | 2025-08-14 | 26.1 | 25 | Completed | -1.1
TSK3215 | Mobile App - Swift | Rohan Gupta | Medium | 2024-04-17 |  | 58.3 | 40 | Open | -18.3
TSK3216 | Marketing Website - Tech | Riya Sharma | High | 2024-07-20 | 2024-08-26 | 69.4 | 93.1 | Completed | 23.7
TSK3217 | E-commerce Platform - Tech | Karan Mehta | Critical | 2025-05-21 | 2025-06-17 | 25 | 19.9 | Completed | -5.1
TSK3218 | POS System - Vivid | Tanvi Desai | Critical | 2023-03-18 | 2023-04-29 | 75.6 | 70.9 | Completed | -4.7
TSK3219 | Marketing Website - Grand | Vikram Joshi | Medium | 2025-01-25 | 2025-02-17 | 15.2 | 20.1 | Completed | 4.9
TSK3220 | Analytics Dashboard - Royal | Aman Verma | Low | 2023-09-10 |  | 42.9 | 32.4 | Open | -10.5
TSK3221 | Analytics Dashboard - Grand | Riya Sharma | Medium | 2024-03-10 | 2024-04-20 | 20.1 | 26.3 | Completed | 6.2
TSK3222 | LMS Platform - Quantum | Isha Bansal | Critical | 2025-01-11 | 2025-02-20 | 51.7 | 79.3 | Completed | 27.6
TSK3223 | Marketing Website - Grand | Siddharth Iyer | High | 2024-10-04 | 2024-11-09 | 34.1 | 21 | Completed | -13.1
TSK3224 | Mobile App - Tech | Isha Bansal | Medium | 2023-07-20 | 2023-09-03 | 54.6 | 76.8 | Completed | 22.2
TSK3225 | Payment Gateway - Cloud | Manish Kumar | High | 2025-02-10 | 2025-02-26 | 17 | 19.1 | Completed | 2.1
TSK3226 | POS System - Silver | Siddharth Iyer | Medium | 2025-06-20 | 2025-07-16 | 37.8 | 31.9 | Completed | -5.9
TSK3227 | Booking System - Silver | Pooja Reddy | Low | 2022-11-21 |  | 8.3 | 7.4 | Open | -0.9
TSK3228 | CRM Integration - Cloud | Siddharth Iyer | Medium | 2022-09-09 | 2022-10-15 | 39.1 | 48.4 | Completed | 9.3
TSK3229 | Inventory Management - Apex | Manish Kumar | Low | 2024-02-10 |  | 52.3 | 15.6 | Open | -36.7
TSK3230 | Analytics Dashboard - Bharat | Riya Sharma | Low | 2023-07-30 | 2023-09-13 | 71.2 | 76.6 | Completed | 5.4
TSK3231 | Analytics Dashboard - Swift | Riya Sharma | Medium | 2025-10-13 | 2025-10-16 | 16 | 23.2 | Completed | 7.2
TSK3232 | Analytics Dashboard - Bright | Aman Verma | High | 2024-11-07 |  | 57.6 | 20.6 | Open | -37
TSK3233 | Inventory Management - Pixel | Ananya Rao | Medium | 2024-02-15 | 2024-03-11 | 54.8 | 62.5 | Completed | 7.7
TSK3234 | Inventory Management - Apex | Manish Kumar | Low | 2024-02-11 | 2024-03-05 | 6.2 | 6.4 | Completed | 0.2
TSK3235 | CRM Integration - Tech | Tanvi Desai | High | 2024-12-03 |  | 76.5 | 27.3 | Open | -49.2
TSK3236 | Website Redesign - Cloud | Ananya Rao | Critical | 2023-10-09 | 2023-11-07 | 40.3 | 38.5 | Completed | -1.8
TSK3237 | POS System - Grand | Tanvi Desai | Medium | 2022-08-13 | 2022-09-07 | 8.7 | 10.6 | Completed | 1.9
TSK3238 | CRM Integration - Apex | Siddharth Iyer | Critical | 2024-05-29 | 2024-06-23 | 57.5 | 70.9 | Completed | 13.4
TSK3239 | CRM Integration - Cloud | Tanvi Desai | High | 2024-08-20 | 2024-08-21 | 75.6 | 79 | Completed | 3.4
TSK3240 | Payment Gateway - Cloud | Ananya Rao | Low | 2025-02-19 | 2025-03-19 | 37 | 42.7 | Completed | 5.7
TSK3241 | Website Redesign - Cloud | Manish Kumar | Critical | 2023-05-22 | 2023-05-28 | 48.6 | 67.3 | Completed | 18.7
TSK3242 | POS System - Swift | Karan Mehta | Medium | 2024-07-27 | 2024-08-02 | 58.5 | 67.8 | Completed | 9.3
TSK3243 | HRMS Portal - Nova | Priya Singh | Critical | 2025-05-07 | 2025-05-27 | 22.9 | 17.1 | Completed | -5.8
TSK3244 | Analytics Dashboard - Swift | Siddharth Iyer | Critical | 2025-09-11 | 2025-09-16 | 30.2 | 46.6 | Completed | 16.4
TSK3245 | Analytics Dashboard - Bright | Ananya Rao | High | 2023-06-19 | 2023-06-26 | 12.6 | 7.6 | Completed | -5
TSK3246 | Booking System - Crest | Manish Kumar | Medium | 2025-03-13 |  | 27.7 | 8.3 | Open | -19.4
TSK3247 | Booking System - Silver | Ananya Rao | High | 2022-08-20 | 2022-10-04 | 17.7 | 16.2 | Completed | -1.5
TSK3248 | Analytics Dashboard - Cloud | Rohan Gupta | Critical | 2023-11-01 | 2023-12-03 | 77.5 | 107.1 | Completed | 29.6
TSK3249 | Analytics Dashboard - Swift | Priya Singh | Low | 2025-09-04 | 2025-10-11 | 17.6 | 28.1 | Completed | 10.5
TSK3250 | Mobile App - Swift | Manish Kumar | Critical | 2024-09-20 | 2024-10-09 | 66.8 | 44.7 | Completed | -22.1
TSK3251 | POS System - Nova | Ananya Rao | Critical | 2024-07-15 | 2024-07-31 | 21.7 | 16.4 | Completed | -5.3
TSK3252 | CRM Integration - Apex | Neha Kapoor | Critical | 2024-08-30 |  | 39.4 | 14.2 | Open | -25.2
TSK3253 | Analytics Dashboard - Royal | Neha Kapoor | Low | 2023-04-08 |  | 30 | 24.2 | Open | -5.8
TSK3254 | Payment Gateway - Cloud | Riya Sharma | Critical | 2025-08-01 | 2025-09-13 | 29.7 | 37 | Completed | 7.3
TSK3255 | HRMS Portal - Urban | Neha Kapoor | Medium | 2024-10-13 | 2024-10-20 | 22.2 | 24.7 | Completed | 2.5
TSK3256 | Mobile App - Tech | Rohan Gupta | Low | 2023-09-12 | 2023-10-26 | 47.9 | 52.7 | Completed | 4.8
TSK3257 | Website Redesign - Pixel | Priya Singh | High | 2024-01-08 | 2024-01-14 | 11.1 | 17.1 | Completed | 6
TSK3258 | POS System - Vivid | Aman Verma | Critical | 2024-06-24 | 2024-07-08 | 42.6 | 40.4 | Completed | -2.2
TSK3259 | Mobile App - Tech | Manish Kumar | High | 2023-08-29 | 2023-09-01 | 65.2 | 46.6 | Completed | -18.6
TSK3260 | Payment Gateway - Cloud | Neha Kapoor | Medium | 2025-07-09 |  | 74.5 | 49.6 | Open | -24.9
TSK3261 | E-commerce Platform - Tech | Ananya Rao | Medium | 2025-02-01 | 2025-03-01 | 76.8 | 63.9 | Completed | -12.9
TSK3262 | POS System - Grand | Karan Mehta | Critical | 2022-08-02 | 2022-08-28 | 4.3 | 5.2 | Completed | 0.9
TSK3263 | Analytics Dashboard - Bright | Tanvi Desai | Low | 2025-01-19 | 2025-02-02 | 18.1 | 24.5 | Completed | 6.4
TSK3264 | E-commerce Platform - Nova | Karan Mehta | Critical | 2025-06-02 |  | 43.9 | 14.5 | Open | -29.4
TSK3265 | Marketing Website - Grand | Arjun Nair | Critical | 2025-11-26 | 2025-12-28 | 43.2 | 53.5 | Completed | 10.3
TSK3266 | Cloud Migration - Apex | Priya Singh | High | 2023-09-01 | 2023-09-24 | 29.5 | 31.2 | Completed | 1.7
TSK3267 | Cloud Migration - Apex | Aman Verma | Medium | 2023-10-22 | 2023-10-31 | 26.4 | 22.1 | Completed | -4.3
TSK3268 | Marketing Website - Tech | Ananya Rao | Critical | 2024-10-25 | 2024-11-19 | 34.6 | 25.5 | Completed | -9.1
TSK3269 | POS System - Grand | Priya Singh | Medium | 2022-06-24 | 2022-08-08 | 73.7 | 112.8 | Completed | 39.1
TSK3270 | Marketing Website - Grand | Manish Kumar | High | 2024-12-12 | 2025-01-02 | 67.7 | 82.6 | Completed | 14.9
TSK3271 | POS System - Swift | Vikram Joshi | Critical | 2024-09-15 | 2024-10-10 | 77.2 | 85.3 | Completed | 8.1
TSK3272 | Marketing Website - Grand | Riya Sharma | Medium | 2025-01-14 | 2025-02-12 | 40.1 | 27.4 | Completed | -12.7
TSK3273 | Analytics Dashboard - Cloud | Arjun Nair | Critical | 2023-05-05 | 2023-06-09 | 24.5 | 33.8 | Completed | 9.3
TSK3274 | E-commerce Platform - Tech | Rohan Gupta | Low | 2025-05-02 | 2025-05-10 | 22.9 | 26.2 | Completed | 3.3
TSK3275 | CRM Integration - Nova | Tanvi Desai | Medium | 2022-06-30 | 2022-07-28 | 10 | 14.3 | Completed | 4.3
TSK3276 | Booking System - Silver | Manish Kumar | Low | 2022-06-07 | 2022-06-30 | 69.3 | 47.6 | Completed | -21.7
TSK3277 | POS System - Swift | Siddharth Iyer | Critical | 2025-05-18 |  | 47.9 | 15.1 | Open | -32.8
TSK3278 | Cloud Migration - Quantum | Arjun Nair | High | 2023-10-31 | 2023-11-14 | 65.5 | 92.1 | Completed | 26.6
TSK3279 | Mobile App - Tech | Sneha Patel | High | 2023-07-18 | 2023-07-29 | 27.2 | 35.5 | Completed | 8.3
TSK3280 | Inventory Management - Apex | Ananya Rao | Low | 2024-01-15 |  | 12.6 | 8.5 | Open | -4.1
TSK3281 | Analytics Dashboard - Swift | Manish Kumar | Medium | 2025-11-10 | 2025-11-19 | 21.5 | 28.2 | Completed | 6.7
TSK3282 | Booking System - Crest | Vikram Joshi | Low | 2023-11-15 | 2023-12-26 | 23 | 23.3 | Completed | 0.3
TSK3283 | CRM Integration - Cloud | Vikram Joshi | Critical | 2022-09-09 | 2022-09-27 | 56.2 | 83 | Completed | 26.8
TSK3284 | Cloud Migration - Tech | Pooja Reddy | High | 2024-12-18 | 2024-12-24 | 59 | 62.4 | Completed | 3.4
TSK3285 | Cloud Migration - Grand | Rohan Gupta | High | 2023-09-10 | 2023-10-08 | 66.3 | 72.6 | Completed | 6.3
TSK3286 | CRM Integration - Tech | Isha Bansal | Low | 2024-11-19 | 2024-12-26 | 68.5 | 95.1 | Completed | 26.6
TSK3287 | Website Redesign - Crest | Priya Singh | Critical | 2025-03-09 | 2025-04-08 | 3.3 | 5 | Completed | 1.7
TSK3288 | HRMS Portal - Grand | Isha Bansal | Medium | 2022-12-02 |  | 35.4 | 31.7 | Open | -3.7
TSK3289 | Booking System - Silver | Rohan Gupta | High | 2022-07-09 |  | 70.4 | 5.9 | Open | -64.5
TSK3290 | Inventory Management - Apex | Sneha Patel | Medium | 2024-01-09 | 2024-02-20 | 14.9 | 14.8 | Completed | -0.1
TSK3291 | Website Redesign - Cloud | Priya Singh | Medium | 2024-10-27 | 2024-11-03 | 2.1 | 2.3 | Completed | 0.2
TSK3292 | E-commerce Platform - Nova | Manish Kumar | Critical | 2025-04-01 | 2025-04-02 | 56.3 | 79.8 | Completed | 23.5
TSK3293 | E-commerce Platform - Vivid | Aman Verma | High | 2025-03-03 | 2025-03-28 | 9 | 12.7 | Completed | 3.7
TSK3294 | Marketing Website - Tech | Aman Verma | Low | 2024-07-16 | 2024-07-25 | 52 | 66.4 | Completed | 14.4
TSK3295 | Cloud Migration - Apex | Priya Singh | Critical | 2023-11-06 | 2023-11-29 | 58.3 | 71.6 | Completed | 13.3
TSK3296 | Cloud Migration - Apex | Tanvi Desai | Low | 2023-11-15 | 2023-11-29 | 8.8 | 6.2 | Completed | -2.6
TSK3297 | Analytics Dashboard - Bright | Sneha Patel | Low | 2025-04-06 | 2025-05-04 | 26.5 | 19.6 | Completed | -6.9
TSK3298 | API Development - Quantum | Riya Sharma | High | 2023-06-29 | 2023-08-07 | 24.2 | 37.3 | Completed | 13.1
TSK3299 | Mobile App - Crest | Riya Sharma | Medium | 2023-08-12 | 2023-08-25 | 60.3 | 54 | Completed | -6.3

## Invoices
invoice_id | client_name | invoice_date | invoice_amount | gst | payment_status | due_date | paid_date | total_amount | is_overdue
INV4000 | Vivid Ventures | 2025-03-01 | 208043.77 | 37447.88 | Unpaid | 2025-03-16 |  | 245491.65 | TRUE
INV4001 | Grand Systems | 2023-01-25 | 748461.03 | 134722.99 | Paid | 2023-02-24 | 2023-02-07 | 883184.02 | FALSE
INV4002 | Silver Systems | 2025-05-11 | 446157.85 | 80308.41 | Paid | 2025-06-10 | 2025-06-05 | 526466.26 | FALSE
INV4003 | Grand Technologies | 2023-05-30 | 478143.53 | 86065.84 | Paid | 2023-06-14 | 2023-06-18 | 564209.37 | FALSE
INV4004 | Pixel Works | 2023-05-04 | 415156.27 | 74728.13 | Paid | 2023-06-03 |  | 489884.4 | FALSE
INV4005 | Vivid Works | 2025-04-30 | 567412.3 | 102134.21 | Paid | 2025-05-30 | 2025-05-23 | 669546.51 | FALSE
INV4006 | Quantum Industries | 2023-11-09 | 85205.72 | 15337.03 | Paid | 2023-12-09 | 2023-11-20 | 100542.75 | FALSE
INV4007 | Quantum Corp | 2023-11-15 | 274865.23 | 49475.74 | Unpaid | 2023-12-30 |  | 324340.97 | TRUE
INV4008 | Cloud Net | 2023-05-16 | 564967.19 | 101694.09 | Overdue | 2023-06-15 |  | 666661.28 | TRUE
INV4009 | Quantum Enterprises | 2023-04-29 | 250000 | 15704.28 | Paid | 2023-05-14 | 2023-05-10 | 265704.28 | FALSE
INV4010 | Silver Ventures | 2023-04-23 | 539542.07 | 97117.57 | Unpaid | 2023-05-23 |  | 636659.64 | TRUE
INV4011 | Crest Hub | 2023-09-02 | 572162.47 | 102989.24 | Overdue | 2023-09-17 |  | 675151.71 | TRUE
INV4012 | Quantum Works | 2025-10-13 | 427944.18 | 77029.95 | Overdue | 2025-11-12 |  | 504974.13 | TRUE
INV4013 | Grand Works | 2024-06-14 | 310058.16 | 55810.47 | Overdue | 2024-06-29 |  | 365868.63 | TRUE
INV4014 | Royal Solutions | 2023-08-30 | 281308.6 | 50635.55 | Paid | 2023-09-14 | 2023-09-08 | 331944.15 | FALSE
INV4015 | Grand Systems | 2024-06-22 | 780539.46 | 140497.1 | Unpaid | 2024-08-06 |  | 921036.56 | TRUE
INV4016 | Vivid Ventures | 2025-07-21 | 300896.64 | 54161.4 | Paid | 2025-09-04 | 2025-08-27 | 355058.04 | FALSE
INV4017 | Quantum Works | 2025-01-23 | 218990.54 | 39418.3 | Paid | 2025-02-07 | 2025-01-30 | 258408.84 | FALSE
INV4018 | Grand Net | 2023-08-25 | 597808.37 | 107605.51 | Paid | 2023-09-09 | 2023-08-23 | 705413.88 | FALSE
INV4019 | Apex Systems | 2024-05-15 | 387976.38 | 69835.75 | Paid | 2024-05-30 | 2024-06-05 | 457812.13 | FALSE
INV4020 | Crest Hub | 2023-03-14 | 646430.08 | 116357.41 | Overdue | 2023-04-28 |  | 762787.49 | TRUE
INV4021 | Urban Works | 2025-05-08 | 271005.57 | 48781 | Paid | 2025-05-23 | 2025-05-10 | 319786.57 | FALSE
INV4022 | Urban Industries | 2024-07-09 | 465798.05 | 83843.65 | Paid | 2024-07-24 | 2024-07-13 | 549641.7 | FALSE
INV4023 | Quantum Labs | 2024-01-03 | 647383.66 | 116529.06 | Partially Paid | 2024-01-18 | 2024-01-11 | 763912.72 | TRUE
INV4024 | Grand Systems | 2025-08-10 | 623351.43 | 112203.26 | Paid | 2025-09-09 | 2025-09-17 | 735554.69 | FALSE
INV4025 | Tech Works | 2025-07-24 | 307757.1 | 55396.28 | Paid | 2024-06-30 | 2025-07-24 | 363153.38 | FALSE
INV4026 | Grand Group | 2024-05-11 | 307253.43 | 55305.62 | Partially Paid | 2024-06-10 | 2024-06-09 | 362559.05 | TRUE
INV4027 | Grand Works | 2024-05-17 | 24974.75 | 4495.45 | Paid | 2024-06-01 | 2024-06-04 | 29470.2 | FALSE
INV4028 | Quantum Industries | 2024-12-10 | 674867.73 | 121476.19 | Partially Paid | 2025-01-24 | 2025-01-19 | 796343.92 | TRUE
INV4029 | Apex Systems | 2025-02-09 | 587227.73 | 105700.99 | Paid | 2025-03-26 | 2025-03-20 | 692928.72 | FALSE
INV4030 | Quantum Enterprises | 2025-05-09 | 769724.35 | 138550.38 | Partially Paid | 2025-06-08 | 2025-06-09 | 908274.73 | TRUE
INV4031 | Bright Technologies | 2024-07-27 | 54242.21 | 9763.6 | Paid | 2024-08-11 | 2024-07-25 | 64005.81 | FALSE
INV4032 | Nova Net | 2025-04-25 | 718550.79 | 129339.14 | Paid | 2025-06-09 | 2025-05-27 | 847889.93 | FALSE
INV4033 | Apex Corp | 2023-07-15 | 124140.8 | 22345.34 | Overdue | 2023-08-29 |  | 146486.14 | TRUE
INV4034 | Grand Systems | 2023-05-08 | 536706.26 | 96607.13 | Paid | 2023-06-07 | 2023-06-08 | 633313.39 | FALSE
INV4035 | Vivid Industries | 2024-10-07 | 566565.97 | 101981.87 | Overdue | 2024-11-06 |  | 668547.84 | TRUE
INV4036 | Urban Industries | 2025-07-16 | 202216.76 | 36399.02 | Partially Paid | 2025-08-15 | 2025-08-16 | 238615.78 | TRUE
INV4037 | Grand Technologies | 2023-08-12 | 102413.05 | 18434.35 | Paid | 2023-08-27 | 2023-08-27 | 120847.4 | FALSE
INV4038 | Grand Enterprises | 2023-09-05 | 299464.21 | 53903.56 | Overdue | 2023-10-20 |  | 353367.77 | TRUE
INV4039 | Cloud Group | 2024-09-23 | 226706.18 | 40807.11 | Paid | 2024-10-23 | 2024-10-28 | 267513.29 | FALSE
INV4040 | Grand Net | 2024-09-15 | 563564.83 | 101441.67 | Paid | 2024-10-30 | 2024-10-14 | 665006.5 | FALSE
INV4041 | Urban Industries | 2023-10-31 | 574702.77 | 103446.5 | Partially Paid | 2023-11-15 | 2023-11-08 | 678149.27 | TRUE
INV4042 | Vivid Works | 2023-04-11 | 253095.75 | 45557.24 | Overdue | 2023-05-26 |  | 298652.99 | TRUE
INV4043 | Crest Hub | 2023-03-05 | 686589.02 | 123586.02 | Unpaid | 2023-04-04 |  | 810175.04 | TRUE
INV4044 | Tech Works | 2024-05-26 | 380393.73 | 68470.87 | Overdue | 2024-06-10 |  | 448864.6 | TRUE
INV4045 | Swift Solutions | 2023-09-06 | 68101.96 | 12258.35 | Overdue | 2023-09-21 |  | 80360.31 | TRUE
INV4046 | Crest Group | 2023-09-25 | 662465.26 | 119243.75 | Paid | 2023-10-10 | 2023-09-30 | 781709.01 | FALSE
INV4047 | Urban Works | 2023-06-22 | 477172.63 | 85891.07 | Partially Paid | 2023-08-06 | 2023-08-09 | 563063.7 | TRUE
INV4048 | Nova Corp | 2023-05-13 | 723946.94 | 130310.45 | Paid | 2023-05-28 | 2023-06-03 | 854257.39 | FALSE
INV4049 | Apex Corp | 2024-11-10 | 53303.13 | 9594.56 | Paid | 2024-11-25 | 2024-11-30 | 62897.69 | FALSE
INV4050 | Silver Systems | 2025-06-06 | 328098.98 | 59057.82 | Paid | 2025-07-21 | 2025-07-10 | 387156.8 | FALSE
INV4051 | Crest Systems | 2023-12-20 | 187478.56 | 33746.14 | Paid | 2024-01-19 | 2024-01-21 | 221224.7 | FALSE
INV4052 | Cloud Group | 2023-11-01 | 499003.13 | 89820.56 | Unpaid | 2023-11-16 |  | 588823.69 | TRUE
INV4053 | Urban Works | 2024-08-27 | 341353.92 | 61443.71 | Unpaid | 2024-09-26 |  | 402797.63 | TRUE
INV4054 | Quantum Labs | 2023-06-29 | 318751.92 | 57375.35 | Paid | 2023-07-29 | 2023-07-19 | 376127.27 | FALSE
INV4055 | Nova Net | 2024-05-25 | 795388.08 | 143169.85 | Paid | 2024-07-09 | 2024-07-19 | 938557.93 | FALSE
INV4056 | Swift Systems | 2025-01-05 | 444723.89 | 80050.3 | Paid | 2025-02-04 | 2025-01-16 | 524774.19 | FALSE
INV4057 | Silver Systems | 2025-10-25 | 322937.39 | 58128.73 | Paid | 2025-11-24 | 2025-11-24 | 381066.12 | FALSE
INV4058 | Bharat Net | 2024-03-24 | 718696.53 | 129365.38 | Overdue | 2024-04-08 |  | 848061.91 | TRUE
INV4059 | Quantum Labs | 2025-08-24 | 298797.66 | 53783.58 | Unpaid | 2025-10-08 |  | 352581.24 | TRUE